TERMS OF REFERENCE

for short-term engagement of ‘team of experts/researchers for mapping active CSOs in BiH per each of EU negotiation chapters’

# I     BACKGROUND

## Beneficiary country

The action will be implemented in Bosnia and Herzegovina.

## Project description

Title: ‘EU for Civil Society (EU4CS) - Capacity building of Governments to include CSOs into the decision-making, Bosnia and Herzegovina'.

The overall objective of this project is to address the problem of weak cooperation and dialogue between governments and civil society in Bosnia and Herzegovina and to extend support to inclusive social dialogue and social partners (employees, employers, governments) including in relation to legislation, collective negotiations, assessing the need for new legislation, drafting the laws and monitoring the implementation of reforms.

The specific objective is to target the problem of weak cooperation and dialogue between governments and civil society in Bosnia and Herzegovina and extend it in direction of support to social dialogue and social partners (employees, employers, governments) including on such issues as legislation, collective negotiations, assessing the need for new legislation, drafting the laws and monitoring the implementation of reforms.

Expected outputs to be achieved include:

- Strengthen capacity of the public institutions and CSOs for better cooperation on policy dialogue,

- Strengthen capacity of the CSOs for better cooperation on creating and drafting strategic, legal and policy framework,

- Improved social dialogue between social partners (employees, employers, governments) at all institutional levels,

- Ensure participations of CSOs in the public consultations process/public debates on different institutional levels,

- Improved transparency in financing of CSOs by public institutions and

- Improved CSOs programme and financial reporting system to relevant institutions.

Project ‘EU for Civil Society (EU4CS) - Capacity building of Governments to include CSOs into the decision-making, Bosnia and Herzegovina', is implemented by international consortium led by PCM Consulting, Igor Stojanovic sp, Voždovačka 4, 78000 Banja Luka, Bosnia and Herzegovina Phone:  +387 51 329560; info@pcm.ba

## Relevant country background

Since 1995 and according to the Dayton Agreement the state of Bosnia and Herzegovina has been divided into two political entities – the Republic of Srpska (RS) and the Federation Bosnia and Herzegovina (FBiH) – and the Brčko District (condominium). The RS covers 49 % of the territory and forms a semi-circle around the north and east, while the FBiH occupies the other 51%. Each Entity has its own political structure and administration. The BiH State government consists of a Parliamentary Assembly, which is divided into a House of Representatives and a House of Peoples, a rotating tripartite Presidency (with one member from each of the constituent peoples – Bosniaks, Croats and Serbs), and a Council of Ministers with nine ministries. The political structure of the FBiH is divided into three levels: the Entity level, the Cantonal level and the Municipal level, with each municipality having its own municipal council and administrative structures. By contrast, the Republic of Srpska (RS) has no cantons, only municipalities.

Therefore, in such a complex environment non-state actors (NSA) have difficulties in advocating for reforms in the above mentioned areas.

According to the latest data obtained from the BiH Ministry of Justice, there are more than 27,000 organisations that can be considered as civil society non-profit organisations. At the State and Federation BiH  level, the Ministries of Justices are responsible for registration and for keeping the Registry Books for Associations and Foundations. According to RS's Law on Associations and Foundations, associations and foundations register at the Basic Court in the seat of the District Court in the area in which they have their seat.

## Current state of affairs in the relevant sector

On the basis of a recommendation by the Commission, in December 2022 the European Council granted Bosnia and Herzegovina the status of candidate country. The positive momentum that followed the granting of candidate status resulted in limited progress on the Opinion’s key priorities.

Following the granting of candidate status, the public commitment of political parties to the strategic goal of European integration brought positive results. Important steps and commitments were made towards the fulfilment of the key priorities, despite negative legislative developments at entity level. The formation of a state-level coalition government at record speed is an important proof of a new political dynamism and will.

Bosnia and Herzegovina is in between an early stage and some level of preparation in its ability to take on the obligations of EU membership. It needs to significantly step up alignment with the EU acquis and implement and enforce the necessary legislation. Limited to no progress was made on most EU acquis chapters during the reporting period.

The Opinion’s key priority 11 on ensuring an enabling environment for civil society still needs to be addressed, notably by upholding European standards on freedom of association and freedom of assembly. Meaningful and systematic consultations with civil society have yet to be ensured as part of an inclusive policy dialogue.

In the context of the upcoming negotiations with the EU, CSOs do not have enough capacity individually, and CSO networking is still at a fairly low level, so the question arises whether CSOs could even articulate a CSO position, which is adequately argued and can produce the desired change, i.e. to influence the representatives of the EU and/or BiH institutions to accept the proposal of the CSO.

During end of 2024 and beginning of 2025, a capacity building process for CSOs about ’Proces of EU integration’ have been realised via technical assistance to CSOs by project EU4CS, funded by European Union. During 10 trainings in various cities, 170 representatives of CSOs and other stakeholders, improved their competences related to the Accession Process (negotiation framework, intergovernmental negotiation conference, screening, criteria for opening, negotiation platform, negotiations and closing chapters, etc.), Methodology of negotiations between states and the EU, Principles of legal harmonization of regulations and ways of participation of CSOs in the negotiation process, as a ground for strengthening the perspective of CSO cooperation with competent authorities at all levels within the negotiation process.

During this trainings cycle, CSOs engaged expressed their readiness to engage in upcoming negotiations process and identified lack of data on existing/competent CSOs per each EU chapter, as obstacle towards development of civic society platform for articulation of CSO engagement in institutional negotiations with EU.

# II     SCOPE OF THE ASSIGNMENT

## 2.1. Description of the assignment

Assignment should include a number of different but complementary components. These include various activities in order to:

    - identify communication data and research status of CSOs regarding their functionality, projects realised within the respective sector(s) and willingness to engage in process of negotiations among EU and BiH,

    - analyse data about CSOs collected and

    - create Report about existing active CSOs per each of EU negotiations chapters, experienced and motivated to engage in/contribute to negotiation process between BiH and EU, and decision making processes during the aligning BiH legislation on all levels with EU acquis.

Number of required experts:

- Non-Key Junior Short-Term Expert/Researcher No1 for researching active CSOs among those registered with Ministry of Justice BiH, Ministry of Justice FBiH and Ministry of Justice and Administration of Sarajevo Canton,

- Non-Key Junior Short-Term Expert/Researcher No 2 for researching active CSOs among those registered with Ministry of Justice and Administration of Herceg-Bosnia Canton, Ministry of Justice and Administration of Central Bosnia Canton, Ministry of Justice and Administration of Tuzla Canton, Ministry of Justice and Administration of West Herzegovina Canton, Ministry of Justice and Administration of the Posavina Canton and RS - Basic Court Prijedor,

- Non-Key Junior Short-Term Expert/Researcher No3 for researching active CSOs among those registered with Ministry of Justice, Administration and Local Self-Government of Herzegovina-Neretva Canton, Ministry of Justice and Administration of Zenica-Doboj Canton, Ministry of Justice and Administration of the Una-Sana Canton, Basic Court of Brcko District BiH and RS - Basic Court Trebinje,

- Non-Key Junior Short-Term Expert/Researcher No4 for researching active CSOs among those registered with RS Basic Courts in Banja Luka, Bijeljina, Doboj and Sokolac.

Duration of the assignment:

- Expert/Researcher No1 - 31 working days

- Expert/Researcher No2 – 30 working days

- Expert/Researcher No3 – 30 working days

- Expert/Researcher No4 – 29 working days

Period of the assignment: January 2026 – April, 2026

Working language: Official languages in BiH

## 2.2. Geographical area

The geographical area to be covered is Bosnia and Herzegovina, including all administrative levels as prescribed above and in accordance with their competences.

## 2.3. Target group

- Public institutions on all levels responsbile for registering CSOs,

- CSOs registered according to Law on Associations and Foundations any of BiH administrative levels,

- EU4CS.

## 2.4. Tasks and deliverables to be provided by the Experts

Envisaged activities include but not limited to:

A: Researching data about active CSOs in BiH:

1/ Preparation phase:

- Finalization of  the research methodology and questionnaire to be used for data gathering from CSOs (via survey, semi-structured phone or online interviews etc.),

- Creation of data base for extracting information collected from CSOs,

- Creation of data base of CSOs’ contacts based on:

- info from http://zbirniregistri.gov.ba/,

- other identified data bases available (e.g. FIA, APIF, data bases on provided

grants to CSOs on various levels, civic society networks etc.) and

- desk research (cross-check based on name of CSOs via internet browsers

and/or social media accounts/presences, exploring CSOs’ web pages, annual

reports etc.) per administrative levels as defined for each of the experts.

B/ Conducting research:

b.1. Collecting data about CSOs via their web pages or email/telephone communication based on earlier developed questionnaire,

B.2. Data extraction into the base and data analysing,

b.2. Monitoring process of data collecting and making weekly data collection progress report,

b.3. Research of other potential sources of data for CSOs and other civic society actors which didn’t respond on research requests (e.g. CSOs’ web sites, annual reports etc.).

C: Creating report

c.1. Drafting Report,

c.2. Presenting draft report to EU4CS,

c.3. Addressing comment and finalization of the report.

Experts will provide the following deliverables:

•	Research methodology and questionnaire for collecting data from CSOs,

•	Data base with filled data on active CSOs,

•	Report on existing active CSOs and their competences disaggregated per EU negotiation chapters as potential participants in negotiation process among BiH and EU and in decision making processes during aligning BiH legislation on all levels with EU acquis.

## 2.5. Payment

The payments will be completed upon the full completion and acceptance of the contract’s obligations, and upon the approval of the Experts’ time and log sheets from the EU programme manager.

# III   REQUIREMENTS

## 3.1. Expert’s profile

Qualifications and skills

- University degree in political/social/technical sciences, public administration, statistic or similar, relevant to this assignment,

- Computer literacy,

- Fluency is BiH languages,

- Fluency in written and spoken English is an advantage.

Professional experience

General professional experience:

- Minimum 5 years of postgraduate professional experience,

Specific professional experience:

- At least 3 years of post-graduate professional experience in area of research or similar related with purpose of this assignment,

- Experience in working in IPA countries (Croatia, The former Yugoslav Republic of Macedonia, Turkey, Albania, Bosnia and Herzegovina, Montenegro, Serbia, and Kosovo (under UNSCR 1244)) will be considered an advantage

Please note that, civil servants and other staff of the public administration of the beneficiary country cannot be recruited as experts, unless prior written approval has been obtained from the European Commission.

# IV  EVALUATION

Received applications from the experts will be evaluated against evaluation criteria developed in line with required qualifications and experiences of the experts, as presented within the section 3 of this ToR.

# V   DOCUMENTS TO BE INCLUDED WHEN SUBMITTING THE PROPOSALS

# 5.1. Applicants shall submit the following documents:

# Personal CV including information on experience in similar projects / assignments

# Application letter to EU4CS confirming interest and availability for the experts per number of trainings with Financial Proposal, indicating fee per working day.

# 5.2. Application Procedure

Applicants interested in applying should submit documents from 5.1. (EU format CV and application letter, both in English) by e-mail to info@eu4cs.ba with a copy to teamleader@eu4cs.ba not later than 16:00 hrs, January 30th, 2026, titled:

Application for the position:

‘Expert/researcher for mapping active CSOs in BiH per each of EU negotiation chapters’

References must be available on request.

Only short-listed candidates will be contacted.

All applications will be considered strictly confidential.

For more information, please contact Igor Stojanovic, Team Leader EU4CS: teamleader@eu4cs.ba.

See http://zbirniregistri.gov.ba/

EU report for BiH 2023 https://neighbourhood-enlargement.ec.europa.eu/bosnia-and-herzegovina-report-2023_en

CPCD, ‘Capacities of organizations civil society in areas of protection environment and the EU integration’ 2024 https://mislioprirodi.ba/wp-content/uploads/2024/04/FINAL-Putujes-li-Evropo_3.pdf

Sarajevo, Banja Luka, Doboj, Brčko, Tuzla, Bihać, Zvornik, Travnik, Trebinje and Mostar

Targeted public institutions to be covered by each of the expert may be reorganized at the beginning of the assignment.