TERMS OF REFERENCE

for short-term engagement of ‘team of experts for supporting realization of Strategy for civic society development of West Herzegovina Canton 2025-2030’

# I     BACKGROUND

## Beneficiary country

The action will be implemented in Bosnia and Herzegovina.

## Project description

Title: ‘EU for Civil Society (EU4CS) - Capacity building of Governments to include CSOs into the decision-making, Bosnia and Herzegovina'.

The overall objective of this project is to address the problem of weak cooperation and dialogue between governments and civil society in Bosnia and Herzegovina and to extend support to inclusive social dialogue and social partners (employees, employers, governments) including in relation to legislation, collective negotiations, assessing the need for new legislation, drafting the laws and monitoring the implementation of reforms.

The specific objective is to target the problem of weak cooperation and dialogue between governments and civil society in Bosnia and Herzegovina and extend it in direction of support to social dialogue and social partners (employees, employers, governments) including on such issues as legislation, collective negotiations, assessing the need for new legislation, drafting the laws and monitoring the implementation of reforms.

Expected outputs to be achieved include:

- Strengthen capacity of the public institutions and CSOs for better cooperation on policy dialogue,

- Strengthen capacity of the CSOs for better cooperation on creating and drafting strategic, legal and policy framework,

- Improved social dialogue between social partners (employees, employers, governments) at all institutional levels,

- Ensure participations of CSOs in the public consultations process/public debates on different institutional levels,

- Improved transparency in financing of CSOs by public institutions and

- Improved CSOs programme and financial reporting system to relevant institutions.

Project ‘EU for Civil Society (EU4CS) - Capacity building of Governments to include CSOs into the decision-making, Bosnia and Herzegovina', is implemented by international consortium led by PCM Consulting, Igor Stojanovic sp, Voždovačka 4, 78000 Banja Luka, Bosnia and Herzegovina Phone:  +387 51 329560; info@pcm.ba

## Relevant country background

Since 1995 and according to the Dayton Agreement the state of Bosnia and Herzegovina has been divided into two political entities – the Republic of Srpska (RS) and the Federation Bosnia and Herzegovina (FBiH) – and the Brčko District (condominium). The RS covers 49 % of the territory and forms a semi-circle around the north and east, while the FBiH occupies the other 51%. Each Entity has its own political structure and administration. The BiH State government consists of a Parliamentary Assembly, which is divided into a House of Representatives and a House of Peoples, a rotating tripartite Presidency (with one member from each of the constituent peoples – Bosniaks, Croats and Serbs), and a Council of Ministers with nine ministries. The political structure of the FBiH is divided into three levels: the Entity level, the Cantonal level and the Municipal level, with each municipality having its own municipal council and administrative structures. By contrast, the Republic of Srpska (RS) has no cantons, only municipalities.

Therefore, in such a complex environment non-state actors (NSA) have difficulties in advocating for reforms in the above mentioned areas.

According to the latest data obtained from the BiH Ministry of Justice, there are more than 27,000 organisations that can be considered as civil society non-profit organisations. At the State and Federation BiH  level, the Ministries of Justices are responsible for registration and for keeping the Registry Books for Associations and Foundations. According to RS's Law on Associations and Foundations, associations and foundations register at the Basic Court in the seat of the District Court in the area in which they have their seat.

## Current state of affairs in the relevant sector

In regards to civil society in BiH, no progress was made in addressing the Opinion key priority 11 on ensuring an enabling environment for civil society, notably by upholding European standards on freedom of association and freedom of assembly. An empowered civil society is a crucial component of any democratic system and should be recognised and treated as such by public institutions. While the overall legal and regulatory framework governing establishment and functioning of civil society organisations is broadly in line with the EU acquis, much remains to be done for public institutions to ensure an enabling environment for civil society, including on freedom of association and of assembly, in line with Opinion key priority 11.

During July 2025, Council of Ministers BiH adopted Strategy of BiH Council of Ministers for creation of a stimulating environment for development of civil society 2025-2029 and initiated its implementation. Also Government of West-Herzegovina Canton (WHC) adopted its Strategy for civic society development 2025-2030 with accompanied Action Plan for 2026-2027 and submitted it for confirmation from the cantonal parliament.

Action plan 2026-2027 among others, proscribe measures for

- Establishing and strengthening institutional mechanisms for cooperation between the government and civil society  including the Development of Guidelines for consultations with CSOs in the process of drafting regulations and other legal acts of the Government of WHC and Model for an online platform for e-consultations,

-  Ensuring a sustainable and transparent system of financing CSOs including  Development of Guidelines on financing CSOs from the County budget, Analysis of existing practices and needs of CSOs regarding co-financing of project proposals and Development of a proposal for a model for the functioning of the co-financing scheme.

Bosnia and Herzegovina needs to ensure meaningful

and systematic consultations with civil society as part of an inclusive policy dialogue and adopt a framework for the transparent funding of civil society organisations, thus ensuring an enabling environment for civil society (Opinion key priority 11).

Action plan for Public Administration Reform in BiH define within its Objective 1 (Strengthening coherence, participation, effectiveness, control and transparency within the system of managing development and decision making in public administration) define obligation of all administrative levels of government to improve process of public participation in creation of public policies (measure 1.4)  and develop e-consultation portal.

# II     SCOPE OF THE ASSIGNMENT

## 2.1. Description of the assignment

Bearing in mind the complexity of development of civic society in WHC and various aspects/approaches for improving environment for work of CSOs planned by the Strategy for civic society development 2025-2030, it is necessary for WHC Government  and its Office for European Integration (as focal point for realization of the Strategy) to dispose of additional professional support in drafting planned legal and other documents (by-laws, analysis, policy proposals etc.) needed to ensure targeted progress in strengthening institutional mechanisms for cooperation among civic society and WHC Government as well as for improving transparency of financing CSOs from WHC budget.

In this regards, the role of the engaged experts is to provide professional support as follows:

    - Public Policy Development Expert - drafting ‘Guidelines for consultations with CSOs in the process of drafting public policies and other legal acts of the Government of WHC’ which is intended to be adopted by the Government of WHC as imperative measure for all public institutions of WHC Government,

    - IT Software Documentation Expert - development of Term of Reference (ToR) for creation of online platform e-consultations of WHC Government, which will be used in later stage as ground for contracting services for creation of the online platform e-consultation, as mechanism for strengthening participation of CSOs and other stakeholders in processes of development public policies in WHC and

    - Financial & Budget Expert - drafting the Guidelines on the financing of CSOs from the budget of WHC  with clearly defined criteria, procedures and monitoring mechanisms, as main framework for further building and realization of the processes for transparent financing of CSOs from the WHC budget.

Number of required experts: 3 Non-Key Short-Term Experts (Public Policy Development Expert, IT Software Documentation Expert and Financial & Budget Expert).

Duration of the assignment:

- Public Policy Development Expert - 16 working days

- IT Software Documentation Expert – 15 working days

- Financial & Budget Expert – 15 working days

Period of the assignment: March 2026 – April 2026

Working language: Official languages in BiH

## 2.2. Geographical area

The geographical area to be covered is West Herzegovina Canton, in accordance with the competences of the Government of West Herzegovina Canton.

## 2.3. Target group

During the process of developing of planned Strategy, the following members of target group are to be engaged (directly in content development and/or during consultations on draft Strategy content):

    - Office of the Government of the West Herzegovina Canton for European Integration;

    - Government of WHC;

    - Assembly of the West Herzegovina Canton;

    - Ministry of Justice, Administration and Digital Transformation of the West Herzegovina Canton;

    - Ministry of Finance;

    - Office of Legislation;

    - Civic Society Organisations;

•     Project EU4CS.

## 2.4. Tasks and deliverables to be provided by the Expert

Tasks description:

- Public Policy Development Expert

- Analysing existing similar public policies on other administrative levels in BiH related with consultations with CSOs in the process of drafting public policies and other legal acts and identification of good practices to be used in WHC,

- Drafting ‘Guidelines for consultations with CSOs in the process of creating public policies and other legal acts of the Government of WHC’ in line with existing legislative framework and via consultations with stakeholders,

- Finalization of  ‘Guidelines for consultations with CSOs in the process of creating public policies and other legal acts of the Government of WHC’ with addressed comments received from stakeholders.

- IT Software Documentation Expert

- Design outline of e-consultation web-platform of WHC Government for performing consultations with CSOs and other interested actors on draft public policies during decision processes in WHC

- Participation in working meetings with representatives of WHC Government’s representatives,

- Preparation of technical specification for e-consultation web platform of WHC Government.

- Financial & Budget Expert

- Analysing existing similar public policies on other administrative levels in BiH related with guidelines on the financing of CSOs from the public budgets and identification of good practices to be used in WHC,

- Mapping and analysing existing practice of WHC Government/ministries/governments’ institutions used for financing CSOs from the budget of WHC,

- Drafting ‘Guidelines on the financing of CSOs from the budget of WHC’  with clearly defined criteria, procedures and monitoring mechanisms’ in line with existing legislative framework and via consultations with stakeholders,

- Finalization of  ‘Guidelines on the financing of CSOs from the budget of WHC’  with clearly defined criteria, procedures and monitoring mechanisms’ with addressed comments received from stakeholders.

Experts will provide the following deliverables:

- Public Policy Development Expert

- Draft Guidelines for consultations with CSOs in the process of creating public policies and other legal acts of the Government of WHC,

- Final draft of Guidelines for consultations with CSOs in the process of creating public policies and other legal acts of the Government of WHC with addressed received comment and accepted by Office of the Government of the WHC for European Integration.

- IT Software Documentation Expert

- Technical specification for development of e-consultation web-platform of WHC Government for performing consultations with CSOs and other interested actors on draft public policies during decision processes in WHC and accepted by Office of the Government of the WHC for European Integration.

- Financial & Budget Expert

- Draft Guidelines on the financing of CSOs from the budget of WHC  ,

- Final draft of ‘Guidelines on the financing of CSOs from the budget of WHC’ with addressed received comment and accepted by Office of the Government of the WHC for European Integration.

## 2.5. Payment

The payments will be completed upon the full completion and acceptance of the contract’s obligations, and upon the approval of the Experts’ time and log sheets from the EU programme manager.

# III   REQUIREMENTS

## 3.1. Expert’s profile

Public Policy Development Expert

Qualifications and skills

- University degree in law, public administration or related field to this assignment,

- Computer literacy;

- Fluency is BiH languages;

- Fluency in written and spoken English is advantage.

Professional experience

General professional experience:

- Minimum 5 years of postgraduate professional experience in area(s) related with this assignment,

Specific professional experience:

- At least 3 years of professional experience in areas related with administrative-legal framework of the Federation BiH or similar related with purpose of this assignment,

- Experience in working in IPA countries (Croatia, Republic of North Macedonia, Turkey, Albania, Bosnia and Herzegovina, Montenegro, Serbia, and Kosovo - under UNSCR 1244) will be considered an advantage.

IT Software Documentation Expert

Qualifications and skills

- University degree in information technologies or related field to this assignment or 5 years general professional experience,

- Computer literacy;

- Fluency is BiH languages;

- Fluency in written and spoken English is advantage.

Professional experience

General professional experience:

- Minimum of  5 years general working experience in IT.

Specific professional experience:

- Minimum of 3 years specific experience of development of project software,

- Experience in working in IPA countries (Croatia, Republic of North Macedonia, Turkey, Albania, Bosnia and Herzegovina, Montenegro, Serbia, and Kosovo - under UNSCR 1244) will be considered an advantage.

Financial & Budget Expert

Qualifications and skills

- University degree in economic or related field to this assignment,

- Computer literacy;

- Fluency is BiH languages;

- Fluency in written and spoken English is advantage.

Professional experience

General professional experience:

- Minimum 5 years of postgraduate professional experience in area(s) related with this assignment,

Specific professional experience:

- At least 3 years of professional experience in areas related with budgeting process, planning and implementation of financial resources, financial transfers to non-profits     on different levels of governments in BiH or similar related with purpose of this assignment,

- Experience in working in IPA countries (Croatia, Republic of North Macedonia, Turkey, Albania, Bosnia and Herzegovina, Montenegro, Serbia, and Kosovo - under UNSCR 1244) will be considered an advantage

Please note that, civil servants and other staff of the public administration of the beneficiary country cannot be recruited as experts, unless prior written approval has been obtained from the European Commission.

# IV  EVALUATION

Received applications from the experts will be evaluated against evaluation criteria developed in line with required qualifications and experiences of the experts, as presented within the section 3 of this ToR.

# V   DOCUMENTS TO BE INCLUDED WHEN SUBMITTING THE PROPOSALS

# 5.1. Applicants shall submit the following documents:

# Personal CV including information on experience in similar projects / assignments

# Application letter to EU4CS confirming interest and availability for the experts per number of trainings with Financial Proposal, indicating fee per working day.

# 5.2. Application Procedure

Applicants interested in applying should submit documents from 5.1. (EU format CV and application letter, both in English) by e-mail to teamleader@eu4cs.ba with a copy to info@eu4cs.ba not later than 16:00 hrs, April 10th, 2026, titled:

Application for the position:

<indicate one of 3 experts’ position you are applying for>

References must be available on request.

Only short-listed candidates will be contacted.

All applications will be considered strictly confidential.

For more information, please contact Igor Stojanovic, Team Leader EU4CS: teamleader@eu4cs.ba

For more details please consult http://zbirniregistri.gov.ba/ (only accessible in Bosnia and

Herzegovina’s official languages)

EU report on BiH for 2022 (https://neighbourhood-enlargement.ec.europa.eu/bosnia-and-herzegovina-report-2022_en)

https://parco.gov.ba/wp-content/uploads/2021/12/akcioni_plan_rju_hr1.pdf